## Ark1
Team | Planning stage |  |  |  | Design | [8 empty] | Build | [10 empty] | Lauch
| 19.08. | 2019-08-20 | 2019-08-21 | 2019-08-22 | 2019-08-23 | 2019-08-26 | 2019-08-27 | 2019-08-29 | 2019-08-30 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-30
Project manager, Developers, photographers | 19.08.: Meeting customer Project start Identifieng goals resources needed project planning
Project manager, Developers, photographers | 2019-08-20: Setting up the teams required
Front-end Developer, photograph. Content developer | 2019-08-20: Research Hardanger and lofthus frukt og saft
Project manager and content developer | 2019-08-22: Find core audience and content planning
Designer, front end developer | 2019-08-23: Design new logo proposal
Front-end developer content developer | 2019-08-23: Site Structure
Photograph | 2019-08-26: Photoshoot of company and hardanger
Photograph, front-end developers designer | 2019-08-29: Style tiles and mood board
Front-end developers | 2019-09-03: Wireframe Mobile version and tablet
Front-end developers | 2019-09-04: Wireframe desktop version
Front-end developers, content developer | 2019-09-06: UI/UX planning and testing with target audience
Front end (css and html team) | 2019-09-10: Coding and building the webpages(html css)
Front end (Java team) | 2019-09-11: Integrating java into the webpages.
designer and content developer | 2019-09-16: Quality check on photos and insertion of written content and video.
Front-End developer, Project manager | 2019-09-18: Presentation to "Lofthus" on the current stage of the project.
Content developer, project manager | 2019-09-23: UX/UI testing
Front end developers. | 2019-09-24: Cross platform and browser testing
Front-End developers | 2019-09-26: Buxfixing
Project manager, content developer | 2019-09-27: Final presentation
Project manger | 2019-09-30: Secure trademark for design and loge
Front end and content developers, project manager, designer, photograph | [30 empty] | Launch!